## JANUARY
EXTERNAL LOANS IN EXECUTION AS OF 01/31/2026
MULTILATERAL FINANCIAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
DNIT | Consolidation of the National Income Tax Office | 2025-01-27 | 7502 | 2025-07-14 | 2031-07-15 | 5 | 30000000 | 561384 | 1.871% | 29438616
ANDE | Rehabilitation and Modernization Program for the Acaray Hydropower Plant | 2019-04-05 | 6492 | 2020-01-02 | 2029-05-07 | 3 | 125000000 | 72017442.8 | 57.61% | 52982557.2
MAG | Implement the Census and Agricultural Surveys System | 2018-05-04 | 6300 | 2019-05-21 | 2027-05-25 | 1 | 15000000 | 12879090.95 | 85.86% | 2120909.05
MEF | Investments in Public Finances for Sustainable Development | 2019-04-05 | 6693 | 2021-01-14 | 2028-01-19 | 2 | 25000000 | 15253333.59 | 61.01% | 9746666.41
MOPC | Rural Road Improvement II | 2016-07-06 | 6022 | 2018-01-05 | 2026-01-17 | 0 | 62000000 | 59915782.92 | 96.64% | 2084217.08
MOPC | Upgrade and Maintenance for National Route 9 and Access Roads | 2018-05-04 | 6151 | 2018-09-18 | 2027-09-20 | 1 | 160000000 | 156551580.07 | 97.84% | 3448419.93
MOPC | Road Corridors Improvement and Maintenance | 2017-07-08 | 6236 | 2018-11-23 | 2027-11-30 | 1 | 90000000 | 67124059.58 | 74.58% | 22875940.42
MOPC | Housing and Rehabilitation for Bañado Sur in Asunción | 2019-04-05 | 6424 | 2019-11-17 | 2027-11-13 | 1 | 100000000 | 15782632.34 | 15.78% | 84217367.66
SENACSA | Improve and Expand Animal Health Services in Paraguay | 2018-11-09 | 6521 | 2020-03-26 | 2026-09-27 | 9 months | 15000000 | 9600759.83 | 64.01% | 5399240.17
SENASA | Water and Sanitation System Construction for Small Cities and Rural and Indigenous Communities in Paraguay | 2017-07-18 | 6144 | 2018-08-23 | 2026-08-29 | 8 months | 40000000 | 37000000 | 92.5% | 3000000
MITIC | Digital Agenda Support | 2018-12-06 | 6298 | 2019-05-06 | 2028-05-08 | 2 | 130000000 | 51903744.44 | 39.93% | 78096255.56
MUVH | Improvement of Housing and Habitat | 2015-11-02 | 5665 | 2016-10-14 | 2026-02-20 | 1 month | 30000000 | 30000000 | 100% | 0
INE | Strengthen Paraguay’s National Statistics System | 2021-08-19 | 6880 | 2021-12-20 | 2026-12-21 | 12 months | 43000000 | 37196478.41 | 86.5% | 5803521.59
MOPC | Rehabilitate and Maintain Agroindustrial Corridors | 2020-05-11 | 6683 | 2020-12-23 | 2027-12-24 | 1 | 235000000 | 210049828.25 | 89.38% | 24950171.75
MOPC | Improve and maintain PY12, from segment Cruce Nanawa to Gral. Bruguez and accesses | 2022-03-16 | 6972 | 2022-09-09 | 2029-09-13 | 3 | 215000000 | 122632657.39 | 57.04% | 92367342.61
AFD | Promoting Private Sector Investments in Energy Efficiency in the Industrial Sector in Paraguay | 2019-02-21 | 6976 | 2022-09-09 | 2027-09-13 | 1 | 20000000 | 2000000 | 10% | 18000000
IPTA | First Individual Program of Finance the Improvement of Research, Innovation, and Transfer of Agricultural Technology in Paraguay | 2020-06-23 | 6904 | 2022-04-29 | 2028-05-03 | 2 | 20000000 | 5020640 | 25.1% | 14979360
MEF | Strengthening the National “Don Carlos Antonio Lopez” Scholarship Program for Postgraduate Studies Abroad | 2020-06-16 | 7025 | 2022-11-02 | 2028-11-23 | 2 | 30000000 | 13975310.13 | 46.58% | 16024689.87
MOPC | Potable Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-26 | 7088 | 2023-05-11 | 2029-05-12 | 3 | 115000000 | 5075752 | 4.414% | 109924248
MSPBS | Strengthen Integrated and Comprehensive Health Services Networks based on Primary Health Care | 2020-03-16 | 7077 | 2023-04-24 | 2029-04-24 | 3 | 45000000 | 4465753.77 | 9.924% | 40534246.23
MOPC | Water and Sanitation for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-05-04 | 7074 | 2023-04-24 | 2029-04-25 | 3 | 105000000 | 3093681 | 2.946% | 101906319
AFD | Access to Financing for Investments in Paraguay´s Agriculture Sector | 2020-03-31 | 7112 | 2023-06-26 | 2028-06-26 | 2 | 30000000 | 18490811 | 61.64% | 11509189
ANDE | Expansion of the High Voltage Transmission System and Energy Efficiency Actions | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 3 | 70000000 | 63674985.8 | 90.96% | 6325014.2
MIC | Support for Business Development Services to Paraguayan Exporting Companies | 2017-07-18 | 6218 | 2018-11-19 | 2026-05-23 | 5 months | 10000000 | 10000000 | 100% | 0
MOPC-MSPBS | Strengthening of the San Estanislao Hospital Services Network | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 4 | 60000000 | 7300000 | 12.17% | 52700000
ANDE | Expansion of the High-voltage Transmission System – Phase II | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3 | 260000000 | 35000000 | 13.46% | 225000000
| TOTAL IADB | [5 empty] | 2080000000 | 1066565708.27 | 51.28% | 1013434291.73
MAG | Market Access for Agricultural Products | 2020-04-14 | 6524 | 2020-03-26 | 2026-06-30 | 6 months | 100000000 | 65230522.39 | 65.23% | 34769477.61
MSPBS | Paraguay Public Health Sector Strengthening | 2019-06-03 | 6523 | 2020-03-26 | 2026-06-30 | 6 months | 115000000 | 88570110.44 | 77.02% | 26429889.56
MOPC | Transport Connectivity | 2016-09-13 | 6025 | 2018-01-05 | 2026-06-15 | 6 months | 100000000 | 91330109.3 | 91.33% | 8669890.7
MOPC | Asuncion Riverfront Urban Resilience | 2023-02-28 | 7201 | 2023-11-24 | 2028-12-29 | 2 | 105000000 | 12117921.25 | 11.54% | 92882078.75
MOPC-MEC | Joining Efforts for an Education of Excellence in Paraguay | 2024-08-07 | 7433 | 2025-01-07 | 2028-12-31 | 2 | 125300000 | 3393137.72 | 2.708% | 121906862.28
| TOTAL IBRD | [5 empty] | 545300000 | 260641801.1 | 47.8% | 284658198.9
MOPC | Local Roads and Bridges - Phase 3 | 2025-05-25 | 7586 | 2025-11-12 | 2031-11-13 | 5 | 74200000 | 0 | 0% | 74200000
ANDE | Improvement for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-26 | 6143 | 2018-08-07 | 2026-12-12 | 12 months | 150000000 | 146771402.61 | 97.85% | 3228597.39
ANDE | National Interconnected System Transmission and Rural Electricity Distribution Strengthening | 2018-10-31 | 6347 | 2019-07-19 | 2026-01-23 | 0 | 170000000 | 161465758.61 | 94.98% | 8534241.39
MOPC | Paved Road Rehabilitation and Maintenance - VIAL 3 | 2017-08-18 | 6235 | 2018-11-23 | 2025-11-29 | 0 | 100000000 | 84582328.04 | 84.58% | 15417671.96
MOPC | Integration Corridor Improvement and Road Reconstruction | 2014-04-04 | 5301 | 2014-10-29 | 2025-06-30 | 0 | 222076000 | 206946285.26 | 93.19% | 15129714.74
MOPC | Enabling the Paved Road Network | 2016-09-28 | 6024 | 2018-01-04 | 2027-01-16 | 1 | 100000000 | 95537813.09 | 95.54% | 4462186.91
MOPC | Construction of Road Access to the Second Bridge with Brazil | 2020-08-24 | 6684 | 2020-12-23 | 2025-12-24 | 0 | 212000000 | 130552856.93 | 61.58% | 81447143.07
ANDE | Electricity Transmission and Distribution System Improvement and Distribution Management Modernization of the Republic of Paraguay | 2020-11-09 | 6876 | 2021-12-16 | 2026-12-16 | 12 months | 250000000 | 112431179.85 | 44.97% | 137568820.15
MOPC | Construction for the Puerto Indio - Superhighway Junction Route, 61 km - Alto Paraná Department - Paraguay | 2020-03-03 | 6897 | 2022-04-01 | 2028-03-03 | 2 | 100000000 | 29595965.42 | 29.6% | 70404034.58
MOPC | Sanitation in Intermediate Cities | 2020-08-18 | 7124 | 2023-07-07 | 2028-07-10 | 2 | 52292000 | 8906954.28 | 17.03% | 43385045.72
MOPC | Rehabilitation, Improvement, and Maintenance for National Route PY22, Concepción, Vallemí, and Access Roads-VIAL 4 | 2024-12-02 | 7517 | 2025-08-06 | 2031-12-31 | 5 | 135000000 | 0 | 0% | 135000000
MOPC | Sanitation Works for the Metropolitan Area of ​​Asunción - Mariano Roque Alonso Basin | 2023-05-04 | 7182 | 2023-10-18 | 2028-10-24 | 2 | 160000000 | 2106524.71 | 1.317% | 157893475.29
| TOTAL CAF | [5 empty] | 1725568000 | 978897068.8 | 56.73% | 746670931.2
MOPC | Paved Road Rehabilitation and Maintenance - VIAL 3 | 2017-08-28 | 6235 | 2018-11-23 | 2025-12-15 | 0 | 42857143 | 42857143 | 100% | 0
MOPC | Enabling the Paved Road Network | 2016-09-27 | 6024 | 2018-01-04 | 2026-02-12 | 1 month | 42750000 | 42750000 | 100% | 0
MOPC | Improvement and Paving for Route PY-15, Section Mariscal Estigarribia - Pozo Hondo and Access to Mariscal Estigarribia in the Department of Boquerón, Republic of Paraguay | 2021-11-16 | 6898 | 2022-04-01 | 2029-04-01 | 3 | 354245764 | 103301935.52 | 29.16% | 250943828.48
MOPC | Improvement of the road section between Pedro Juan Caballero – Capitán Bado – Itanará – Ypejhú in the departments of Amambay and Canindeyú in the Republic of Paraguay | 2020-04-27 | 7119 | 2023-07-06 | 2028-07-14 | 2 | 220000000 | 39527297 | 17.97% | 180472703
ANDE | Construction for the 220 kV Villa Hayes - Villa Real - Pozo Colorado - Loma Plata transmission line and the 220 kV Pozo Colorado Substation in the Western Region | 2023-03-10 | 7153 | 2023-09-15 | 2027-09-15 | 1 | 45000000 | 25235163 | 56.08% | 19764837
| TOTAL FONPLATA | [5 empty] | 704852907 | 253671538.52 | 35.99% | 451181368.48
MOPC | Rehabilitation, Improvement, and Maintenance for National Route PY22, Concepción, Vallemí, San Lázaro, and Access Roads-VIAL 4 | 2024-11-22 | 7517 | 2025-08-06 | 2031-12-31 | 5 | 50000000 | 0 | 0% | 50000000
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 0 | 21600000 | 21565834.04 | 99.84% | 34165.96
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement | 2017-02-20 | 6023 | 2018-01-05 | 2026-12-31 | 12 months | 10400000 | 4385267.83 | 42.17% | 6014732.17
| TOTAL OFID | [5 empty] | 82000000 | 25951101.87 | 31.65% | 56048898.13
ANDE | Improvement for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-11 | 6143 | 2018-08-07 | 2027-12-13 | 2.3699 | 94000000 | 60762535.57 | 64.64% | 33237464.43
| TOTAL BEI | [5 empty] | 94000000 | 60762535.57 | 64.64% | 33237464.43
TOTAL MULTILATERAL FINANCIAL ORGANIZATIONS | [6 empty] | 5231720907 | 2646489754.13 | 50.59% | 2585231152.87
OFFICIAL BILATERAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
AFD | "Che Róga Pora" | 2025-02-14 | 7510 | 2025-07-10 | 2028-02-14 | 2 | 200000000 | 40000000 | 20% | 160000000
| TOTAL EXIMBANK | [5 empty] | 200000000 | 40000000 | 20% | 160000000
SENASA | Potable Water and Sanitation for Small Cities and Rural and Indigenous Communities | 2017-07-18 | 6144 | 2018-08-23 | 2026-08-19 | 8 months | 20000000 | 19056241.61 | 95.28% | 943758.39
MOPC | Water and Sanitation for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-04-26 | 7074 | 2023-04-24 | 2031-01-22 | 5 | 60000000 | 2076364 | 3.461% | 57923636
| TOTAL ICO | [5 empty] | 80000000 | 21132605.61 | 26.42% | 58867394.39
MOPC | Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-27 | 7088 | 2023-05-11 | 2029-05-12 | 3 | 59044169.9541 | 3333402.7679 | 5.646% | 55710767.1862
ANDE | Improving Efficiency of the National Electric Power System | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 3 | 60104766.2161 | 55760984.195 | 92.77% | 4343782.0211
| TOTAL JICA | [5 empty] | 119148936.1702 | 59094386.9629 | 49.6% | 60054549.2073
ANDE | Construction of the 220 kV Transmission Line Villa Hayes - Villa Real – Pozo Colorado - Loma Plata and the 220 kV Pozo Colorado Substation, in the Western Region. | 2022-12-29 | 7153 | 2023-09-15 | 2028-12-31 | 2 | 75000000 | 0 | 0% | 75000000
| TOTAL KFW | [5 empty] | 75000000 | 0 | 0% | 75000000
ANDE
| The High-Voltage Transmission System Expansion (Paraguay) | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3 | 30000000 | 21100000 | 70.33% | 8900000
| TOTAL ICDF | [5 empty] | 30000000 | 21100000 | 70.33% | 8900000
MDN | Procurement of Aerial Platforms (Aircraft) with Advanced Technological Capabilities for the Defense of National Airspace and Support in Counter-Narcoterrorism Operations | 2024-11-19 | 7479 | 2025-05-30 | 2028-06-28 | 2 | 101606009 | 65614833.66 | 64.58% | 35991175.34
| TOTAL BNDES | [5 empty] | 101606009 | 65614833.66 | 64.58% | 35991175.34
TOTAL FOREIGN GOVERMENT FINANCIAL INSTITUTIONS | [6 empty] | 605754945.1702 | 206941826.2329 | 34.16% | 398813118.9373
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
MEF | Resilience and Sustainability (RSF) | 2023-12-18 | 7412 | 2024-12-23 | 2026-02-28 | 1 month | 414441000 | 317186580 | 76.53% | 97254420
| TOTAL FMI | [5 empty] | 414441000 | 317186580 | 76.53% | 97254420
TOTAL FMI
[7 empty] | 414441000 | 317186580 | 76.53% | 97254420
TOTAL EXTERNAL LOANS IN EXECUTION | [6 empty] | 6251916852.1702 | 3170618160.3629 | 50.71% | 3081298691.8073
*Update of disbursements made from the year 2010 to 01/31/2026, according to SIGADE report 02/26/2026, 09:00 AM. - Exchange Rate: 01/30/2026 - Preliminary figures, subject to revision. Exchange Rate (RSF): 01/30/2026

## FEBRUARY
EXTERNAL LOANS IN EXECUTION AS OF 02/28/2026
MULTILATERAL FINANCIAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
DNIT | Consolidation of the National Income Tax Office | 2025-01-27 | 7502 | 2025-07-14 | 2031-07-15 | 5 | 30000000 | 561384 | 1.871% | 29438616
ANDE | Rehabilitation and Modernization Program for the Acaray Hydropower Plant | 2019-04-05 | 6492 | 2020-01-02 | 2029-05-07 | 3 | 125000000 | 72017442.8 | 57.61% | 52982557.2
MAG | Implement the Census and Agricultural Surveys System | 2018-05-04 | 6300 | 2019-05-21 | 2027-05-25 | 1 | 15000000 | 12879090.95 | 85.86% | 2120909.05
MEF | Investments in Public Finances for Sustainable Development | 2019-04-05 | 6693 | 2021-01-14 | 2028-01-19 | 2 | 25000000 | 15253333.59 | 61.01% | 9746666.41
MOPC | Rural Road Improvement II | 2016-07-06 | 6022 | 2018-01-05 | 2026-01-17 | 0 | 62000000 | 59915782.92 | 96.64% | 2084217.08
MOPC | Upgrade and Maintenance for National Route 9 and Access Roads | 2018-05-04 | 6151 | 2018-09-18 | 2027-09-20 | 1 | 160000000 | 156551580.07 | 97.84% | 3448419.93
MOPC | Road Corridors Improvement and Maintenance | 2017-07-08 | 6236 | 2018-11-23 | 2027-11-30 | 1 | 90000000 | 77349363.04 | 85.94% | 12650636.96
MOPC | Housing and Rehabilitation for Bañado Sur in Asunción | 2019-04-05 | 6424 | 2019-11-17 | 2027-11-13 | 1 | 100000000 | 30793472.09 | 30.79% | 69206527.91
SENACSA | Improve and Expand Animal Health Services in Paraguay | 2018-11-09 | 6521 | 2020-03-26 | 2026-09-27 | 8 meses | 15000000 | 9600759.83 | 64.01% | 5399240.17
SENASA | Water and Sanitation System Construction for Small Cities and Rural and Indigenous Communities in Paraguay | 2017-07-18 | 6144 | 2018-08-23 | 2026-08-29 | 7 meses | 40000000 | 37000000 | 92.5% | 3000000
MITIC | Digital Agenda Support | 2018-12-06 | 6298 | 2019-05-06 | 2028-05-08 | 2 | 130000000 | 51903744.44 | 39.93% | 78096255.56
MUVH | Improvement of Housing and Habitat | 2015-11-02 | 5665 | 2016-10-14 | 2026-02-20 | 0 | 30000000 | 30000000 | 100% | 0
INE | Strengthen Paraguay’s National Statistics System | 2021-08-19 | 6880 | 2021-12-20 | 2026-12-21 | 11 meses | 43000000 | 38909056.35 | 90.49% | 4090943.65
MOPC | Rehabilitate and Maintain Agroindustrial Corridors | 2020-05-11 | 6683 | 2020-12-23 | 2027-12-24 | 1 | 235000000 | 210049828.25 | 89.38% | 24950171.75
MOPC | Improve and maintain PY12, from segment Cruce Nanawa to Gral. Bruguez and accesses | 2022-03-16 | 6972 | 2022-09-09 | 2029-09-13 | 3 | 215000000 | 122632657.39 | 57.04% | 92367342.61
AFD | Promoting Private Sector Investments in Energy Efficiency in the Industrial Sector in Paraguay | 2019-02-21 | 6976 | 2022-09-09 | 2027-09-13 | 1 | 20000000 | 2000000 | 10% | 18000000
IPTA | First Individual Program of Finance the Improvement of Research, Innovation, and Transfer of Agricultural Technology in Paraguay | 2020-06-23 | 6904 | 2022-04-29 | 2028-05-03 | 2 | 20000000 | 5020640 | 25.1% | 14979360
MEF | Strengthening the National “Don Carlos Antonio Lopez” Scholarship Program for Postgraduate Studies Abroad | 2020-06-16 | 7025 | 2022-11-02 | 2028-11-23 | 2 | 30000000 | 13975310.13 | 46.58% | 16024689.87
MOPC | Potable Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-26 | 7088 | 2023-05-11 | 2029-05-12 | 3 | 115000000 | 5075752 | 4.414% | 109924248
MSPBS | Strengthen Integrated and Comprehensive Health Services Networks based on Primary Health Care | 2020-03-16 | 7077 | 2023-04-24 | 2029-04-24 | 3 | 45000000 | 4465753.77 | 9.924% | 40534246.23
MOPC | Water and Sanitation for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-05-04 | 7074 | 2023-04-24 | 2029-04-25 | 3 | 105000000 | 3093681 | 2.946% | 101906319
AFD | Access to Financing for Investments in Paraguay´s Agriculture Sector | 2020-03-31 | 7112 | 2023-06-26 | 2028-06-26 | 2 | 30000000 | 18490811 | 61.64% | 11509189
ANDE | Expansion of the High Voltage Transmission System and Energy Efficiency Actions | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 3 | 70000000 | 63674985.8 | 90.96% | 6325014.2
MIC | Support for Business Development Services to Paraguayan Exporting Companies | 2017-07-18 | 6218 | 2018-11-19 | 2026-05-23 | 4 meses | 10000000 | 10000000 | 100% | 0
MOPC-MSPBS | Strengthening of the San Estanislao Hospital Services Network | 2024-04-15 | 7403 | 2024-12-19 | 2030-04-15 | 4 | 60000000 | 7300000 | 12.17% | 52700000
ANDE | Expansion of the High-voltage Transmission System – Phase II | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3 | 260000000 | 35000000 | 13.46% | 225000000
| TOTAL IADB | [5 empty] | 2080000000 | 1093514429.42 | 52.57% | 986485570.58
MAG | Market Access for Agricultural Products | 2020-04-14 | 6524 | 2020-03-26 | 2027-12-31 | 1 | 90000000 | 65230522.39 | 72.48% | 24769477.61
MSPBS | Paraguay Public Health Sector Strengthening | 2019-06-03 | 6523 | 2020-03-26 | 2026-06-30 | 5 meses | 115000000 | 88570110.44 | 77.02% | 26429889.56
MOPC | Transport Connectivity | 2016-09-13 | 6025 | 2018-01-05 | 2026-06-15 | 5 meses | 100000000 | 91330109.3 | 91.33% | 8669890.7
MOPC | Asuncion Riverfront Urban Resilience | 2023-02-28 | 7201 | 2023-11-24 | 2028-12-29 | 2 | 105000000 | 12117921.25 | 11.54% | 92882078.75
MOPC-MEC | Joining Efforts for an Education of Excellence in Paraguay | 2024-08-07 | 7433 | 2025-01-07 | 2028-12-31 | 2 | 125300000 | 3393137.72 | 2.708% | 121906862.28
| TOTAL IBRD | [5 empty] | 535300000 | 260641801.1 | 48.69% | 274658198.9
MOPC | Local Roads and Bridges - Phase 3 | 2025-05-25 | 7586 | 2025-11-12 | 2031-11-13 | 5 | 74200000 | 0 | 0% | 74200000
ANDE | Improvement for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-26 | 6143 | 2018-08-07 | 2026-12-12 | 11 meses | 150000000 | 146771402.61 | 97.85% | 3228597.39
ANDE | National Interconnected System Transmission and Rural Electricity Distribution Strengthening | 2018-10-31 | 6347 | 2019-07-19 | 2026-01-23 | 0 | 170000000 | 161465758.61 | 94.98% | 8534241.39
MOPC | Paved Road Rehabilitation and Maintenance - VIAL 3 | 2017-08-18 | 6235 | 2018-11-23 | 2025-11-29 | 0 | 100000000 | 89906328.04 | 89.91% | 10093671.96
MOPC | Integration Corridor Improvement and Road Reconstruction | 2014-04-04 | 5301 | 2014-10-29 | 2025-06-30 | 0 | 222076000 | 206946285.26 | 93.19% | 15129714.74
MOPC | Enabling the Paved Road Network | 2016-09-28 | 6024 | 2018-01-04 | 2027-01-16 | 1 | 100000000 | 96651605.02 | 96.65% | 3348394.98
MOPC | Construction of Road Access to the Second Bridge with Brazil | 2020-08-24 | 6684 | 2020-12-23 | 2025-12-24 | 0 | 212000000 | 133507856.93 | 62.98% | 78492143.07
ANDE | Electricity Transmission and Distribution System Improvement and Distribution Management Modernization of the Republic of Paraguay | 2020-11-09 | 6876 | 2021-12-16 | 2026-12-16 | 11 meses | 250000000 | 121931179.85 | 48.77% | 128068820.15
MOPC | Construction for the Puerto Indio - Superhighway Junction Route, 61 km - Alto Paraná Department - Paraguay | 2020-03-03 | 6897 | 2022-04-01 | 2028-03-03 | 2 | 100000000 | 32170693.3 | 32.17% | 67829306.7
MOPC | Sanitation in Intermediate Cities | 2020-08-18 | 7124 | 2023-07-07 | 2028-07-10 | 2 | 52292000 | 8906954.28 | 17.03% | 43385045.72
MOPC | Rehabilitation, Improvement, and Maintenance for National Route PY22, Concepción, Vallemí, and Access Roads-VIAL 4 | 2024-12-02 | 7517 | 2025-08-06 | 2031-12-31 | 5 | 135000000 | 0 | 0% | 135000000
MOPC | Sanitation Works for the Metropolitan Area of ​​Asunción - Mariano Roque Alonso Basin | 2023-05-04 | 7182 | 2023-10-18 | 2028-10-24 | 2 | 160000000 | 2106524.71 | 1.317% | 157893475.29
| TOTAL CAF | [5 empty] | 1725568000 | 1000364588.61 | 57.97% | 725203411.39
MOPC | Paved Road Rehabilitation and Maintenance - VIAL 3 | 2017-08-28 | 6235 | 2018-11-23 | 2025-12-15 | 0 | 42857143 | 42857143 | 100% | 0
MOPC | Enabling the Paved Road Network | 2016-09-27 | 6024 | 2018-01-04 | 2026-02-12 | 0 | 42750000 | 42750000 | 100% | 0
MOPC | Improvement and Paving for Route PY-15, Section Mariscal Estigarribia - Pozo Hondo and Access to Mariscal Estigarribia in the Department of Boquerón, Republic of Paraguay | 2021-11-16 | 6898 | 2022-04-01 | 2029-04-01 | 3 | 354245764 | 103301935.52 | 29.16% | 250943828.48
MOPC | Improvement of the road section between Pedro Juan Caballero – Capitán Bado – Itanará – Ypejhú in the departments of Amambay and Canindeyú in the Republic of Paraguay | 2020-04-27 | 7119 | 2023-07-06 | 2028-07-14 | 2 | 220000000 | 39527297 | 17.97% | 180472703
ANDE | Construction for the 220 kV Villa Hayes - Villa Real - Pozo Colorado - Loma Plata transmission line and the 220 kV Pozo Colorado Substation in the Western Region | 2023-03-10 | 7153 | 2023-09-15 | 2027-09-15 | 1 | 45000000 | 25235163 | 56.08% | 19764837
| TOTAL FONPLATA | [5 empty] | 704852907 | 253671538.52 | 35.99% | 451181368.48
MOPC | Rehabilitation, Improvement, and Maintenance for National Route PY22, Concepción, Vallemí, San Lázaro, and Access Roads-VIAL 4 | 2024-11-22 | 7517 | 2025-08-06 | 2031-12-31 | 5 | 50000000 | 0 | 0% | 50000000
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement | 2017-02-20 | 6023 | 2018-01-05 | 2025-12-31 | 0 | 21600000 | 21565834.04 | 99.84% | 34165.96
ANDE | Metropolitan Area Electricity Transmission and Distribution System Improvement | 2017-02-20 | 6023 | 2018-01-05 | 2026-12-31 | 11 meses | 10400000 | 4385267.83 | 42.17% | 6014732.17
| TOTAL OFID | [5 empty] | 82000000 | 25951101.87 | 31.65% | 56048898.13
ANDE | Improvement for the Electricity Transmission and Distribution System of the Metropolitan System of Paraguay (Phase II) | 2017-12-11 | 6143 | 2018-08-07 | 2027-12-13 | 2.3699 | 94000000 | 60762535.57 | 64.64% | 33237464.43
| TOTAL BEI | [5 empty] | 94000000 | 60762535.57 | 64.64% | 33237464.43
TOTAL MULTILATERAL FINANCIAL ORGANIZATIONS | [6 empty] | 5221720907 | 2694905995.09 | 51.61% | 2526814911.91
OFFICIAL BILATERAL ORGANIZATIONS
(in United States dollars)
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
AFD | "Che Róga Pora" | 2025-02-14 | 7510 | 2025-07-10 | 2028-02-14 | 2 | 200000000 | 40000000 | 20% | 160000000
| TOTAL EXIMBANK | [5 empty] | 200000000 | 40000000 | 20% | 160000000
SENASA | Potable Water and Sanitation for Small Cities and Rural and Indigenous Communities | 2017-07-18 | 6144 | 2018-08-23 | 2026-08-19 | 7 meses | 20000000 | 19056241.61 | 95.28% | 943758.39
MOPC | Water and Sanitation for the Metropolitan Area of Asunción - Lambaré Watershed | 2022-04-26 | 7074 | 2023-04-24 | 1931-01-22 | 5 | 60000000 | 2076364 | 3.461% | 57923636
| TOTAL ICO | [5 empty] | 80000000 | 21132605.61 | 26.42% | 58867394.39
MOPC | Water and Sanitation for the Metropolitan Area of Ciudad del Este | 2020-08-27 | 7088 | 2023-05-11 | 2029-05-12 | 3 | 58495643.2599 | 3297153.9052 | 5.637% | 55198489.3547
ANDE | Improving Efficiency of the National Electric Power System | 2021-08-18 | 7147 | 2023-09-15 | 2029-09-15 | 3 | 59546386.4685 | 55490176.9974 | 93.19% | 4056209.4711
| TOTAL JICA | [5 empty] | 118042029.7283 | 58787330.9026 | 49.8% | 59254698.8258
ANDE | Construction of the 220 kV Transmission Line Villa Hayes - Villa Real – Pozo Colorado - Loma Plata and the 220 kV Pozo Colorado Substation, in the Western Region. | 2022-12-29 | 7153 | 2023-09-15 | 2028-12-31 | 2 | 75000000 | 0 | 0% | 75000000
| TOTAL KFW | [5 empty] | 75000000 | 0 | 0% | 75000000
ANDE
| The High-Voltage Transmission System Expansion (Paraguay) | 2023-01-26 | 7414 | 2024-12-23 | 2029-01-26 | 3 | 30000000 | 21100000 | 70.33% | 8900000
| TOTAL ICDF | [5 empty] | 30000000 | 21100000 | 70.33% | 8900000
MDN | Procurement of Aerial Platforms (Aircraft) with Advanced Technological Capabilities for the Defense of National Airspace and Support in Counter-Narcoterrorism Operations | 2024-11-19 | 7479 | 2025-05-30 | 2028-06-28 | 2 | 101606009 | 65614833.66 | 64.58% | 35991175.34
| TOTAL BNDES | [5 empty] | 101606009 | 65614833.66 | 64.58% | 35991175.34
TOTAL FOREIGN GOVERMENT FINANCIAL INSTITUTIONS | [6 empty] | 604648038.7283 | 206634770.1726 | 34.17% | 398013268.5558
EXECUTING AGENCY | PROJECT/PROGRAM NAME | CONTRACT SIGNING DATE | LAWS |  | FINAL DISBURSEMENT DATE | YEARS REMAINING FOR FINAL DISBURSEMENT | TOTAL EXTERNAL AMOUNT | DISBURSEMENT* |  | UNDISBURSED BALANCE
EJECUTOR |  |  | N° | DATE |  |  |  | TOTAL | %
MEF | Resilience and Sustainability (RSF) | 2023-12-18 | 7412 | 2024-12-23 | 2026-02-28 | 0 | 414441000 | 317186580 | 76.53% | 97254420
| TOTAL FMI | [5 empty] | 414441000 | 317186580 | 76.53% | 97254420
TOTAL FMI
[7 empty] | 414441000 | 317186580 | 76.53% | 97254420
TOTAL EXTERNAL LOANS IN EXECUTION | [6 empty] | 6240809945.7283 | 3218727345.2626 | 51.58% | 3022082600.4658
*Update of disbursements made from the year 2010 to 02/28/2026, according to SIGADE report 03/20/2026, 09:00 AM. - Exchange Rate: 02/27/2026 - Preliminary figures, subject to revision. Exchange Rate (RSF): 02/27/2026